## Introduction
'ERICA'
Wildfire Exercise 2014
Protectively marked : NOT PROTECTIVELY MARKED - but intended only for exercise staff
Andy Elliott, Dorset Fire and Rescue Service
18th October 2014

## Executive Budget
Exercise ERICA executive budget sheet
Estimated budget for exercise ERICA.
Exercise preparation and set up
Plan Writing & meetings
Burn Team expenses
Travel claims (meetings etc.)
Casualty Union
Straw bales for burning
Food and refreshment
Exercise planning phase
Exercise day
Equipment
Orienteering stamps
GPS and maps for pre planning
Consumables
Props used with scenarios
Printing
Fuel
Staff Costs (Exercise Day)
WDS Staff
RDS Pay Claims
0
Note on A31: Author: Based on 10 pumps, 8 L4ts and 1 CSU = 70 RDS staff x 6 hours = 420 hrs at £ 12/hr = £5040.

## Objectives
Exercise objective
Manage on site resources via ICS
Examine consistency of approach to similar incidents by different agencies.
Evaluate regional SOP on wildfire
Demonstrate multi agency response to a wildfire incident including the use of UHP and WPNIA partners and outside agency Subject Matter Experts
Support decision making by using external Subject Matter Experts
Communicate effectively.
Evaluate the use of MDTs and paper maps to effectively navigate to remote, off road locations.

## Planning Team Contacts
Planning team | Organisation | Phone | Email

## Master events list (hidden)
Master events list |  |  |  |  | Exercise 'Osprey' 9th October 2011
Time | Exercise control | Weather / Flood info | Tactical coordination | Strategic coordination | National resilience | SAR cell | Police | Local authority | Command function | Logistics function | Rescue teams | HART | Ambulance | Fire | Health | Ambulance
Pre exercise start state
Weather warnings
Exercise starts
Exercise free play
Exercise ends
Note on N3: Author:

## Timeline
|  | Red text | Milestone which must be achieved and may require intervention from excon
|  | Amber text | Milestone which is important to an agency but not critical to the agency
|  | ACTION | Something that will be done regardless of players activity
|  | INJECT | Prompt generated from Excon
[5 empty] | 0800 | 1000 | 1200 | 1400 | 1600 | 1800 | 0800 | 1000 | 1200 | 1300 | 1400 | 1500 | 1600 | 1700
| Tuesday 14th |  | Wednesday 15th | Thursday 16th | Friday 17th |  | Midday |  |  |  | Saturday 18th AM |  | Midday |  |  |  |  | Close
Excon | ACTION…. What : exercise build up FSI Why : Scene setting for all players Who : Met Office How : Email |  | ACTION…. What : exercise build up FSI Why : Scene setting for all players Who : Met Office How : Email | ACTION…. What : exercise build up FSI Why : Scene setting for all players Who : Met Office How : Email | ACTION…. What : exercise build up FSI Why : Scene setting for all players Who : Met Office How : Email | Burn team to prepare burn plots and assess likely fire behaviour for ERICA. Forestry Commission, John Dold and Andy Elliott | INJECT : DFRS/UHP Press release |  | ACTION…. What : Fire behaviour report Why : Decision required on scale of live burn exercise Who : John Dold - Burn Team Supervisor. How : Email | Final decisions taken re. Proceeding with exercise based on weather forecast and fire behaviour report. |  | Orienteering markers in place ready for the start of the exercise. | Operational command in place with Command Support 17 up and running. | Orienteering and site scenarios up and running |  | Live burn exercises to start. | Operational ENDEX after orienteering and firefighting tasks have been completed.
| ACTION…. What : Review weather forecast Why : Go / no go decision for exercise operational elements Who : EXCON (Julian Lockwood/Andy Elliott) How : Hazard Manager website |  | ACTION…. What :Exercise build up Drought Warning Why : Scene setting for all players Who : Met Office How : Email | ACTION…. What : Exercise build up Media Interest Why : Scene setting for all players Who : Excon - Via media team How : Email video file of news item | ACTION…. What :Exercise build up Drought Warning Why : Scene setting for all players Who : Met Office How : Email | [5 empty] | Observer programme in place for operational command and scenarios | Operational command begins setting up | Exercise safety brief delivered to all teams at RVP and at operational command. | Command Support 17 managing incident and issuing instructions to appliances |  |  | ACTION…. What : Hot debrief Why : Evaluate the exercise while information is fresh Who : EXCON (all locations) How : Face to face
|  |  |  | ACTION…. What :Exercise build up Drought Warning Why : Scene setting for all players Who : Met Office How : Email | [6 empty] | ACTION…. What : exercise build up FSI Why : Scene setting for all players Who : Met Office How : Email | Operational scenarios constructed and safety checked as necessary. | Safety and observer teams are in place at the operational command site and ready to receive appliances. | Incident Command Team up and running |  |  | Tactical endex at discretion of EXCON once sufficient evidence gathered to evaluate exercise objectives.
[11 empty] | ACTION…. What :Exercise build up Drought Warning Why : Scene setting for all players Who : Met Office How : Email |  | INJECT : Media briefing required
ACTION…. What : On site feeding for personnel Why : Lunch time! Who : EXCON for all locations How : Welfare vehicle, Packed Lunch? TBC
Fire |  |  | Duty silver given background context explaining the significance and risk associated with the scenario and weather conditions. | Some consultation with advisors and teams within the fire service. May begin to allocate roles and tasks. May begin to seek specialist advice from colleagues in the County. | Business continuity implications for emergency response to multiple or large wildfires. | INJECT: Media interest in wildfire risk. Consider a Joint Press Release with UHP and Dorset Police via Operation Heathland. |  | Inject : What are the welfare and safety arrangements for staff working at wildfires? |  |  |  | Fire reported in Wareham Forest | Teams are briefed on incident, command structure, communications, ongoing threat from weather and other hazards as well as locations of operational command. | Scenario: A crew has come across a member of the public that has serious head injuries after falling from their mountain bike. | Scenario-Crews have been working hard since time of call and require feeding, rest or relief. THIS CREW WILL BE FIRST CALL FOR REAL INCIDENT | Scenario: being directed to the XXX flank in an attempt to suppress the fire. | Scenario: Backpacks and hand tools in use to damp down hotspots on tail.
|  |  |  | Considers internal preparedness for extreme wildfire behaviour. | [7 empty] | 10:15 Make Pumps five, L4ts four, Unimog 1 | Operational command team, vehicles and systems in place and operating. | Inject : A firefighter has received serious burns while fighting a gorse fire in 'dress down' kit. | INJECT - Cover issues around county due to number of incidents and current deployment of appliances | Scenario: required to reinforce fuel break on XXX flank. | Inject: Appliance XXX has failed to respond to repeated radio calls and their whereabouts are unknown.
[12 empty] | 11:00 Make pumps 10 (heavy off road if possible) L4ts 10, Unimog 1 and Water Carriers 2 | Fire ground technology - remote cameras operating and images / video visible at both operational and tactical commands. | Scenario : An L4t has become stuck and is being threatened by an approaching fire front. | Inject: Fire is spreading towards the A35 with large amounts of smoke crossing the highway | Inject: Crews working on head fire are requesting relief as they are exhausted. Also request Ambulance for collapsed crew member. | JESIP?
[13 empty] | Subject matter advisors (Wildfire) being consulted | Inject: Multiple ignition points being reported by crews. It is thought that a person or persons are still on site setting fires. | INJECT: For Command Team; High winds forecast for 18:00 | Scenario: HVP/Water Carrier to set up Water Sector to replenish tank.
FC
|  |  | Consider erecting 'Severe Fire Risk' signs at entry points to the forest. | [8 empty] | Fire reported in Wareham Forest | Large incident declared and ICM established |  | Deploy large plant to assist with control line construction | Estimate damage to forest including crop
Investigate the availability of large plant
Ranger deployed to assist DFRS
Dorset Local Authority
|  |  | Severe Weather Warning re. Drought conditions received and distributed to LRF by DEPO | Severe Weather Warning re. Drought conditions received and distributed to LRF by DEPO |  | Severe Weather Warning re. Drought conditions received and distributed to LRF by DEPO | [5 empty] | Severe Weather Warning re. Drought conditions received and distributed to LRF by DEPO | DCC Bronze Liaison Officer deployed to Wareham Forest | DEPO to liaise with Dorset Police re. Possible evacuations and road closures | DCC Bronze Liaison Officer notified of smoke plume crossing the A35. police considering road closure. |  |  | Debriefing
DEPO to consider public health impacts due to poor air conditions as a result of smoke.
SWAST | [11 empty] | Notified of large wildfire at Wareham Forest | HART team deployed to Wareham Forest | Inject: A crew has come across a member of the public that has serious head injuries after falling from their mountain bike. |  | Crews working on head fire are requesting relief as they are exhausted. Also request Ambulance for collapsed crew member. |  | Debriefing
[12 empty] | Bronze Liaison Officer deployed to Wareham Forest |  | Inject : A firefighter has received serious burns while fighting a gorse fire in 'dress down' kit.
Police
|  |  |  | Made aware of extreme wildfire risk by DFRS | Business continuity implications for emergency response and other core business considered | DFRS request a joint Press Release from DFRS, Police and UHP via Operation Heathland | [5 empty] | Informed of large wildfire at Wareham Forest by DFRS | Assess likely life risk. Are there members of public in Wareham Forest? Are there residential or commercial properties that may require evacuation? Are there any roads that may require closing/controlling? |  | Notified by 999 and DFRS that smoke is crossing the A35. DFRS state that the fire is currently heading in that direction. |  |  | Debriefing
[6 empty] | Consider calling an extraordinary meeting of Operation Heathland | [5 empty] | Bronze Liaison Officer deployed to Wareham Forest

## People, Assets, Venues
People, Assets and Venues
Back to Planners Overview
|  | Thursday |  | Friday
Venue | Function | Open | Closed | Open | Closed | Notes
Wareham Forest Cold Harbour Offices | Host command and incident scenario preparation and execution. | 1000hrs | 1700hrs | 1000hrs | 1800hrs | Site visits required
Wareham Forest RVP | Command Support, welfare including food etc. | x | x | 1000hrs | 1800hrs | Site visits required
Dorset Fire HQ (DFRSHQ) | Accommodation for tactical command and exercise control | x | x | 0800hrs | 1900hrs | Rooms and parking to be booked
|  | Thursday |  | Friday
Person or asset | Likely role | numbers | location | numbers | location | Notes / requirements for people assets or technologies
FIRE Gold officer | Passive gold / observer |  |  |  |  | TBC
Fire Silver officers | Representative at TCG, offsite silver command, on site silver for Friday |  |  |  |  | To be booked through diary system.
Fire Bronze officers | Various support roles at TCG, Command Support / management |  |  |  |  | To be booked through diary system
FIRE Staff | General support for major incident centre and to fire silver
FIRE firefighters | General support for major incident centre, SHA and incident
FIRE control operator | Fire control involvement, comms, call management | [5 empty] | Cost
FIRE control team | Command and control | [5 empty] | Cost | CS17
FIRE Excon | Exercise control, observers and safety |  |  |  |  | Needs office space, IT facilities, internet connection, mobile, airwave and landline communications.
FIRE Observers | Observers only
HART Manager | Observer
Vehicle PCV | Observer transport, safety / observer team transport and shelter. Logistics support
Vehicle VAN | General transport, feeding, welfare and logistics

## Partner Agencies
Partner Agencies
| Principle contact | Mobilised by
Fire Operations |  | Dorset Fire
Fire Control |  | Dorset Fire
Police |  | Dorset Police
HART (SWAST) |  | EXCON
Forestry Commission |  | EXCON
Urban Heaths Partnership |  | EXCON
WPNIA |  | EXCON
FireLab |  | EXCON

## Scenario Background
Scenario background
The UK has experienced a second very dry year with surface water levels very low in many areas. Deep frosts over prolonged periods during the winter have further reduced the moisture content in the fuels. The last few weeks have seen no rainfall with a stiff easterly breeze drying out the fuels. In addition a strong sun has raised the temperature and reduced the relative humidity.
To provide a credible weather scenario which would threaten wildfire prone landscapes in Dorset and that may lead to large wildfires with the evacuation of properties and road closures.
Weather warnings available from Monday to help set scene
Met Office Fire Severity Index should show that the fine fuels, duff and soil are very dry. Fires are likely to spread rapidly and will be difficult to suppress.
FSI severe conditions due to peak on Friday and last through the weekend when the wind is expected to increase from the east.
Media
There have been a number of incidents in recent weeks around the UK and in Dorset. These have been widely reported in the media as the dry conditions persist.
Video clip of media coverage of wildfires.
Video clip to criticise preparation of emergency services
Request for interview / statement to be presented pm on both Thursday and Friday, this interview / statement to be recorded and played back within TCG

## Injects (hidden)
Injects | Back to Planners Overview
Detailed injects if not covered in timeline

## Education (hidden)
Education | Back to Planners Overview
Each organisation will ensure that their players are suitably briefed for the exercise. Likely subject areas include;
Flooding
Major incident procedures
Flood rescue coordination
Strategic holding areas
Internal emergency procedures
Use of CLIO (web based software used to coordinate incidents within the LRF area)
Working within a tactical coordination centre

## Evaluation (hidden)
Evaluation | Back to Planners Overview
Design of evaluation techniques to measure objectives.

## Pre arranged Assets (hidden)
Pre arraged assets
Rescue teams , logisical support and advisors pre booked. | Back to Planners Overview

## Real Cover (hidden)
Real cover
National guidance to ensure sufficient cover for real event. | Back to Planners Overview

## SCG (hidden)
SCG
Simulated by pre prepared minutes and responses by excon as needed.
Back to Planners Overview
Detail here
Excon will simulate SCG responses as needed, individual agencies may choose to involve their gold players, but there will not be an SCG meeting

## Strategy (hidden)
Strategy
Covered here
Back to Planners Overview

## TCG (hidden)
TCG | Back to Planners Overview
Real play based on pre briefing.
Venue, members, support staff and comms / information.
? Scope of this group i.e. dealing with flood water etc or just rescues.

## SAR Cell (hidden)
SAR CELL | Back to Planners Overview
Real play based on TCG direction.
Venue, members, support staff and comms / information

## Comms (hidden)
Comms | Back to Planners Overview
CLIO, Airwave
Sitrep, ? managing rescue tasks.

## Information (hidden)
Information | Back to Planners Overview
GIS
Flood and weather situation
Local flood plans

## Tasks (hidden)
Tasks | Back to Planners Overview
Emergency calls
Proactive vulnerable people assistance

## Media (hidden)
Media | Back to Planners Overview
Media pre event brief (real( and during play involvment (simulated)

## Holding Area (hidden)
Holding area | Back to Planners Overview
Venue
Enhanced logistical support (FRS capability)
Reception point

## Manage Resources (hidden)
Manage resources
Long term operation
Team accreditation | Back to Planners Overview
Duty of care
Cost
Food / welfare

## Command (hidden)
Command
Real play at one venue with local joint command linking to tatcical level.
Who is in charge / responsible
Back to Planners Overview

## Specific tasks
Orienteering tasks
Crews deployed from Rendezvous Point then sent on a variety of tasks to test their ability to find and navigate to locations using MDTs and paper maps. | Back to Planners Overview
Tasks and operational injects | Rationale
Task 1: Go to point XXX measure the are indicated by the boundary marker tape and pass the details via radio to Command Support. | To confirm the ability of the crew to accurately estimate/measure area at a wildfire incident.
Task 2: Move to point XXX describe the likely fire behaviour of the incident described on the card using the Wildfire Prediction System factors of alignment. | To confirm the ability of the crews to apply the WIPs (Wildfire Prediction System) to determine the most likely fire behaviour.
Task 3: Move to point XXX. Your crew have been allocated as the safety crew for the incident described on the card. Identify the most suitable escape routes for the crews already deployed and the safety zones that they should make for in the event of an emergency. Pass these details to command Support via radio. | To confirm the ability of the crews to apply the LACES protocol to determine the safest options working at a wildfire.
Task 4: Move to point XXX. You discover a cyclist that has fallen from their cycle in an attempt to leave the area. Deal with the incident and report back to Command Support as required. | Cyclist to have severe head injuries. Also to have with him/her the paraphernalia for starting wildfires. Crews to demonstrate ability to manage casualty and identify the need to preserve evidence and notify Command Support of their findings.
ICS Tasks | Back to Planners Overview
Command Team expected to utilise expertise of Land Managers and liaise with the FC Command Team and other agencies.
Tasks and operational injects | Rationale
Task ICS1: Brief command team on extent of fire using OTHERS as if a change of OiC.
Task ICS2: Request OiC for a tactical plan to manage fire.
Task ICS3: Request likely extent of fire and potential control lines.
Task ICS4: Media briefing and interview required
Inject ICS1: A crew has come across a member of the public that has serious head injuries after falling from their mountain bike.
Inject ICS2: A firefighter has received serious burns while fighting a gorse fire in 'dress down' kit.
Inject ICS4: An L4t has become stuck and is being threatened by an approaching fire front.
Inject ICS5: Multiple ignition points being reported by crews. It is thought that a person or persons are still on site setting fires
Inject ICS6: Crews have been working hard since time of call and require feeding, rest or relief.
Inject ICS7: Cover issues around county due to number of incidents and current deployment of appliances
Inject ICS8: Fire is spreading towards the A35 with large amounts of smoke crossing the highway
Inject ICS9: For Command Team; High winds forecast for 18:00
Inject ICS10: Crews being directed to the XXX flank in an attempt to suppress the fire.
Inject ICS11: CAFFs required to reinforce fuel break on XXX flank.
Inject ICS12: Crews working on head fire are requesting relief as they are exhausted. Also request Ambulance for collapsed crew member.
Inject ICS13: Backpacks and hand tools in use to damp down hotspots on tail.
Inject ICS14: Appliance XXX has failed to respond to repeated radio calls and their whereabouts are unknown.
Inject ICS15: Request from Police; is there a requirement to close any roads or to evacuate members of the public from homes or within the forest itself?
Firefighting Tasks | Back to Planners Overview
Tasks and operational injects | Rationale
Task Ff1: Crews to have a smouldering fire to extinguish with hand tools and backpacks if available. | Burn team to set a series of buried smouldering fires in stumps etc. Use charcoal to simulate fire spread underground. This is to be detected by the crews using TiC and dug out to extinguish.
Task Ff2: Crews to create a control line using CAFFs and or water. | Area suitable for creating a control line alongside an existing fuel break or track. Ideally to use CAFFs and or water, but provide opportunities for them to use hand tools to remove taller vegetation such as gorse.
Task Ff3: Crews to extinguish a fire in undergrowth using suitable techniques. | Burn team to create a fire that can be tackled from a safe anchor point and then along each flank towards the head. This will be determined by conditions on the day. Ideally this element to be recorded on video for later de-brief.
TaskFf4: Crews to establish a water supply in the field suitable to replenish the tanks of appliances.